## 3 Nov 2022
Date: 3 November 2022
Time: 4:30PM - 5:30PM
Present Project team: CNC - Melissa Boey, Elizabeth Yeo, Tess Hng Pharmacy - Raymond Liew, Chong Yi San, Tan Mei Xin, Tan Li Ling, Sharon Yeo Taggle: Seng Beo, James, Rochin + 1
Discussion Points | Action By
1. Follow-up discussion with nurses regarding Calculator
Yi San discussed with Sr Joyce that prescribed frequency for the medical consumables may change frequently for diabetes patients. E.g. they may prescribe a specific frequency first visit but if patient insulin control turns out to be poor, then they may have to review the prescribed frequency in the next visit. | FYI
Yi San discussed with Raymond on 2 options to handle this: (1) Do not include prescribed frequency as part of the patient profile as this value may change frequently. Clinician will have to input this prescribed frequency value in the ordering page, each time they make an order (2) Alternatively, include prescribed frequency as part of patient profile (but optional for clinician user to input). Patient profile to read value from latest prescribed order and update patient profile value. For next order, ordering page should auto-populate value from patient profile (if any value is present in the profile page) should the item be prescribed, but allow clinician to update the prescribed frequency at the ordering page, should changes need to be made. The latest value in the ordering page to be updated to the patient profile again after each confirmed order. | FYI: Decided to go with option (2)
To input calculator and frequency of medication for informative purposes | Taggle
2. Consumable Profile
Regarding sorting control, Taggle has listed the permutations | FYI
To make the quantity field editable so that user does not have to keep reducing or adding by 1 each time | Taggle
3. Calculator
Algorithm has not been input in prototype yet. | FYI
Output refers to total units required, Minimum Quantity to Prescribe refers to minimum package that needs to be ordered. | FYI
Taggle to set up calculator | Taggle
4. Login Matters
Currently, login is via ADID | FYI
KIV to allow Corp Pass access in future | FYI
5. MSW Dashboard
For MediFund, sometimes patients have pending approval - Memo may state interim approval; pharmacy will provide medication based on memo - Current terminology in dashboard doesn’t have ‘interim approval' - Suggestions for wordings: Active, Expired, Pending | FYI
Interim to be added as an option under 'Status' - no need to manually edit in the system when funding is over, system will automatically update | Taggle
There are multiple types of funds: - Medifund - SMTA/ PA/ MFEC card assistance | FYI
To insert another column for funding type - to split into 'funding type' and 'approval duration' | Taggle
Situations where funding would be deactivated: - Deceased/banned from hospital etc. Situations where funding would be deactivated: - Deceased/banned from hospital etc. | FYI
To set default expiry of voucher as 1 year or voucher from MSW (whichever is shorter) | Taggle
To think about what should be done for patients with no known assistance yet, but want to redeem/purchase medication | All
6. Redeem Voucher Segment
To include on the voucher whther it is funded or self-payment so it is clear for the patient | Taggle
Self-payment to be in red | Taggle
To include details of voucher (e.g. how many % co-payment etc.) | Taggle
7. Others
TTSH team to run through the prototype and collate feedback for Seng Beo by next week. | TTSH Staff
Prototype link: https://mjamesm23.github.io/eWallet_calculator/